## regression
Task 1: The regression set of your application consists of 2000 tests. You have only 200 times. Describe your course of action.
Steps for choosing regression tests:
1. Select the TC with the highest priority;
2. Select the TC that had bugs;
3. Select TC checking new functionality;
4. Select the TCs that check the functionality that could be affected by the corrected bugs;
5. Select the TC checking the functionality that is most used by the site visitor.

## risk matrix
Task 2: Draw a risk matrix when testing a new build with a new functionality
# | risk | severity | likelyhood | impact | mitigation | contigency
1 | the developer gave the build at the wrong time | 2 | 0.5 | 0.7 | agree with the development team on deadline | shift release date
2 | smoke testing is blocked up | 3 | 0.7 | 0.5 | introduce unit tests | build rebuild
3 | critical defects in the new functionality | 1 | 0.5 | 0.8 | implement unit tests for developers | critical defects are reported directly to the developer
4 | half the testers team got sick | 2 | 0.4 | 0.6 | take on one employee more | work overtime
5 | incorrect estimate | 2 | 0.7 | 0.7 | reastimization | shift release date
Values in the "likelyhood" and "impact" column mean 0.1 the smallest impact and likelyhood, 1.0 the greatest